COSC2671 Assignment 2 Worksheet

Project plan, timesheets and self-reflection

Course level: PG| Group: Group 37

# 1. Team project plan

| Item | Plan |
| --- | --- |
| Project aim | Analyse YouTube fan communities and sentiment around the 2025 Australian Grand Prix using NLP and network analysis. |
| Data source | Public YouTube videos and comments collected with YouTube Data API v3. |
| Main tasks | Collect data, clean comments, conduct sentiment/topic analysis, construct reply network, calculate centrality, detect communities, write report and prepare presentation. |
| Tools | Python, pandas, NLTK/VADER, scikit-learn LDA, NetworkX, matplotlib, wordcloud, Jupyter Notebook. |
| Risk controls | Do not submit API keys, pseudonymise users, include representative sample only, document platform/API limitations. |

# 2. Work breakdown

| Team member | Main responsibilities |
| --- | --- |
| Anjana / 4139491 | Notebook integration, data collection workflow, NLP analysis, network analysis, report drafting and review. |
| Sona / s4137524 | Data Preprocessing |
| Melvin / S4185713 | Information diffusion |

# 3. Weekly timesheet template

| Week | Member | Tasks completed | Evidence / output |
| --- | --- | --- | --- |
| Week 1 | Anjana | Group formation | Notebook/report commits |
| Week 1 | Sona | Group formation, reviewed A1 codebase, set up shared drive, discussed project scope | Meeting notes/drive commits |
| Week 1 | Melvin | Group formation | Meeting notes/drive commits |
| Week 2 | Anjana | Topic selection / Sample project testing | Notebook/report commits |
| Week 2 | Sona | Refined research questions, planned data pipeline, tested YouTube API quota limits | Meeting notes/drive commits |
| Week 2 | Melvin | Milestone tracker setup, timesheet template created, coordinated task distribution | timesheets.xlsx, management/ folder |
| Week 3 | Anjana | Notebook integration, data collection workflow, NLP analysis, network analysis, report drafting and review, Centrality analysis, clustering coefficients, network visualisations, Louvain community detection, community characterization. | Notebook/report commits |
| Week 3 | Sona | Built fetch pipeline (fetchYoutubeData.py), collected 30 videos, preprocessed comments, pseudonymised user IDs | agp2025_raw.json, comments_clean.csv |
| Week 3 | Melvin | Researched IC diffusion model, studied NetworkX diffusion implementation, maintained timesheets | Meeting notes |
| Week 4 | Anjana | Report sections (Discussion, Conclusion, Limitations, References), compiled worksheet, coordinated Access.txt submission | Notebook/report commits |
| Week 4 | Sona | Report, VADER sentiment analysis (4 visualisations), LDA topic modelling (5 topics), temporal sentiment analysis, cross-topic analysis | sentiment_distribution.png, lda_topics.png |
| Week 4 | Melvin | Report , Built diffusion.py — Independent Cascade model on user-user network, vanilla IC implementation | diffusion.py |

# 4. Individual self-reflection – Anjana

I contributed to the project by developing and organising the Python notebook, collecting and cleaning YouTube comment data, and implementing the NLP and network analysis workflow. I learned that social media networks can be structurally sparse even when the text dataset is large, so visualisations must be interpreted carefully rather than treated as evidence by themselves. The main challenge was connecting the project question to both text and network evidence without overclaiming that network position strongly predicts sentiment. The final results show a clear answer: AGP YouTube discussion has strong fan participation and identifiable interaction hubs, but sentiment is only weakly related to network position.